## Akende aastaplaan
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Akende aastaplaan | Kinnitatud AS Eesti Raudtee juhatuse 18.04.2023 otsusega nr 698/2. | [16 empty] | jaanuar
Enter Company Name in cell B2. | Eesti Raudtee | [57 empty] | veebruar | [19 empty] | märts | [29 empty] | aprill | [32 empty] | mai | [31 empty] | juuni | [28 empty] | juuli | [29 empty] | august | [28 empty] | september | [30 empty] | oktoober | [31 empty] | november | [27 empty] | detsember
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | 2023 | Project Start: |  | öised aknad | [534 empty] | 1900-03-05 | [6 empty] | 1900-03-12 | [6 empty] | 1900-03-19 | [6 empty] | 1900-03-26 | [6 empty] | 1900-04-02
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: | 1 | ööpäevaringsed aknad | [380 empty] | 1901-01-07 | [6 empty] | 1901-01-14 | [6 empty] | 1901-01-21 | [6 empty] | 1901-01-28 | [6 empty] | 1901-02-04 | [6 empty] | 1901-02-11 | [6 empty] | 1901-02-18 | [6 empty] | 1901-02-25 | [6 empty] | 1901-03-04 | [6 empty] | 1901-03-11 | [6 empty] | 1901-03-18 | [6 empty] | 1901-03-25 | [6 empty] | 1901-04-01 | [6 empty] | 1901-04-08 | [6 empty] | 1901-04-15 | [6 empty] | 1901-04-22 | [6 empty] | 1901-04-29 | [6 empty] | 1901-05-06 | [6 empty] | 1901-05-13 | [6 empty] | 1901-05-20 | [6 empty] | 1901-05-27 | [6 empty] | 1901-06-03 | [6 empty] | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23 | 1900-03-24 | 1900-03-25 | 1900-03-26 | 1900-03-27 | 1900-03-28 | 1900-03-29 | 1900-03-30 | 1900-03-31 | 1900-04-01 | 1900-04-02 | 1900-04-03 | 1900-04-04 | 1900-04-05 | 1900-04-06 | 1900-04-07 | 1900-04-08
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | [6 empty] | -5 | -4 | -3 | -2 | -1 | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23 | 1900-03-24 | 1900-03-25 | 1900-03-26 | 1900-03-27 | 1900-03-28 | 1900-03-29 | 1900-03-30 | 1900-03-31 | 1900-04-01 | 1900-04-02 | 1900-04-03 | 1900-04-04 | 1900-04-05 | 1900-04-06 | 1900-04-07 | 1900-04-08 | 1900-04-09 | 1900-04-10 | 1900-04-11 | 1900-04-12 | 1900-04-13 | 1900-04-14 | 1900-04-15 | 1900-04-16 | 1900-04-17 | 1900-04-18 | 1900-04-19 | 1900-04-20 | 1900-04-21 | 1900-04-22 | 1900-04-23 | 1900-04-24 | 1900-04-25 | 1900-04-26 | 1900-04-27 | 1900-04-28 | 1900-04-29 | 1900-04-30 | 1900-05-01 | 1900-05-02 | 1900-05-03 | 1900-05-04 | 1900-05-05 | 1900-05-06 | 1900-05-07 | 1900-05-08 | 1900-05-09 | 1900-05-10 | 1900-05-11 | 1900-05-12 | 1900-05-13 | 1900-05-14 | 1900-05-15 | 1900-05-16 | 1900-05-17 | 1900-05-18 | 1900-05-19 | 1900-05-20 | 1900-05-21 | 1900-05-22 | 1900-05-23 | 1900-05-24 | 1900-05-25 | 1900-05-26 | 1900-05-27 | 1900-05-28 | 1900-05-29 | 1900-05-30 | 1900-05-31 | 1900-06-01 | 1900-06-02 | 1900-06-03 | 1900-06-04 | 1900-06-05 | 1900-06-06 | 1900-06-07 | 1900-06-08 | 1900-06-09 | 1900-06-10 | 1900-06-11 | 1900-06-12 | 1900-06-13 | 1900-06-14 | 1900-06-15 | 1900-06-16 | 1900-06-17 | 1900-06-18 | 1900-06-19 | 1900-06-20 | 1900-06-21 | 1900-06-22 | 1900-06-23 | 1900-06-24 | 1900-06-25 | 1900-06-26 | 1900-06-27 | 1900-06-28 | 1900-06-29 | 1900-06-30 | 1900-07-01 | 1900-07-02 | 1900-07-03 | 1900-07-04 | 1900-07-05 | 1900-07-06 | 1900-07-07 | 1900-07-08 | 1900-07-09 | 1900-07-10 | 1900-07-11 | 1900-07-12 | 1900-07-13 | 1900-07-14 | 1900-07-15 | 1900-07-16 | 1900-07-17 | 1900-07-18 | 1900-07-19 | 1900-07-20 | 1900-07-21 | 1900-07-22 | 1900-07-23 | 1900-07-24 | 1900-07-25 | 1900-07-26 | 1900-07-27 | 1900-07-28 | 1900-07-29 | 1900-07-30 | 1900-07-31 | 1900-08-01 | 1900-08-02 | 1900-08-03 | 1900-08-04 | 1900-08-05 | 1900-08-06 | 1900-08-07 | 1900-08-08 | 1900-08-09 | 1900-08-10 | 1900-08-11 | 1900-08-12 | 1900-08-13 | 1900-08-14 | 1900-08-15 | 1900-08-16 | 1900-08-17 | 1900-08-18 | 1900-08-19 | 1900-08-20 | 1900-08-21 | 1900-08-22 | 1900-08-23 | 1900-08-24 | 1900-08-25 | 1900-08-26 | 1900-08-27 | 1900-08-28 | 1900-08-29 | 1900-08-30 | 1900-08-31 | 1900-09-01 | 1900-09-02 | 1900-09-03 | 1900-09-04 | 1900-09-05 | 1900-09-06 | 1900-09-07 | 1900-09-08 | 1900-09-09 | 1900-09-10 | 1900-09-11 | 1900-09-12 | 1900-09-13 | 1900-09-14 | 1900-09-15 | 1900-09-16 | 1900-09-17 | 1900-09-18 | 1900-09-19 | 1900-09-20 | 1900-09-21 | 1900-09-22 | 1900-09-23 | 1900-09-24 | 1900-09-25 | 1900-09-26 | 1900-09-27 | 1900-09-28 | 1900-09-29 | 1900-09-30 | 1900-10-01 | 1900-10-02 | 1900-10-03 | 1900-10-04 | 1900-10-05 | 1900-10-06 | 1900-10-07 | 1900-10-08 | 1900-10-09 | 1900-10-10 | 1900-10-11 | 1900-10-12 | 1900-10-13 | 1900-10-14 | 1900-10-15 | 1900-10-16 | 1900-10-17 | 1900-10-18 | 1900-10-19 | 1900-10-20 | 1900-10-21 | 1900-10-22 | 1900-10-23 | 1900-10-24 | 1900-10-25 | 1900-10-26 | 1900-10-27 | 1900-10-28 | 1900-10-29 | 1900-10-30 | 1900-10-31 | 1900-11-01 | 1900-11-02 | 1900-11-03 | 1900-11-04 | 1900-11-05 | 1900-11-06 | 1900-11-07 | 1900-11-08 | 1900-11-09 | 1900-11-10 | 1900-11-11 | 1900-11-12 | 1900-11-13 | 1900-11-14 | 1900-11-15 | 1900-11-16 | 1900-11-17 | 1900-11-18 | 1900-11-19 | 1900-11-20 | 1900-11-21 | 1900-11-22 | 1900-11-23 | 1900-11-24 | 1900-11-25 | 1900-11-26 | 1900-11-27 | 1900-11-28 | 1900-11-29 | 1900-11-30 | 1900-12-01 | 1900-12-02 | 1900-12-03 | 1900-12-04 | 1900-12-05 | 1900-12-06 | 1900-12-07 | 1900-12-08 | 1900-12-09 | 1900-12-10 | 1900-12-11 | 1900-12-12 | 1900-12-13 | 1900-12-14 | 1900-12-15 | 1900-12-16 | 1900-12-17 | 1900-12-18 | 1900-12-19 | 1900-12-20 | 1900-12-21 | 1900-12-22 | 1900-12-23 | 1900-12-24 | 1900-12-25 | 1900-12-26 | 1900-12-27 | 1900-12-28 | 1900-12-29 | 1900-12-30 | 1900-12-31 | 1901-01-01 | 1901-01-02 | 1901-01-03 | 1901-01-04 | 1901-01-05 | 1901-01-06 | 1901-01-07 | 1901-01-08 | 1901-01-09 | 1901-01-10 | 1901-01-11 | 1901-01-12 | 1901-01-13 | 1901-01-14 | 1901-01-15 | 1901-01-16 | 1901-01-17 | 1901-01-18 | 1901-01-19 | 1901-01-20 | 1901-01-21 | 1901-01-22 | 1901-01-23 | 1901-01-24 | 1901-01-25 | 1901-01-26 | 1901-01-27 | 1901-01-28 | 1901-01-29 | 1901-01-30 | 1901-01-31 | 1901-02-01 | 1901-02-02 | 1901-02-03 | 1901-02-04 | 1901-02-05 | 1901-02-06 | 1901-02-07 | 1901-02-08 | 1901-02-09 | 1901-02-10 | 1901-02-11 | 1901-02-12 | 1901-02-13 | 1901-02-14 | 1901-02-15 | 1901-02-16 | 1901-02-17 | 1901-02-18 | 1901-02-19 | 1901-02-20 | 1901-02-21 | 1901-02-22 | 1901-02-23 | 1901-02-24 | 1901-02-25 | 1901-02-26 | 1901-02-27 | 1901-02-28 | 1901-03-01 | 1901-03-02 | 1901-03-03 | 1901-03-04 | 1901-03-05 | 1901-03-06 | 1901-03-07 | 1901-03-08 | 1901-03-09 | 1901-03-10 | 1901-03-11 | 1901-03-12 | 1901-03-13 | 1901-03-14 | 1901-03-15 | 1901-03-16 | 1901-03-17 | 1901-03-18 | 1901-03-19 | 1901-03-20 | 1901-03-21 | 1901-03-22 | 1901-03-23 | 1901-03-24 | 1901-03-25 | 1901-03-26 | 1901-03-27 | 1901-03-28 | 1901-03-29 | 1901-03-30 | 1901-03-31 | 1901-04-01 | 1901-04-02 | 1901-04-03 | 1901-04-04 | 1901-04-05 | 1901-04-06 | 1901-04-07 | 1901-04-08 | 1901-04-09 | 1901-04-10 | 1901-04-11 | 1901-04-12 | 1901-04-13 | 1901-04-14 | 1901-04-15 | 1901-04-16 | 1901-04-17 | 1901-04-18 | 1901-04-19 | 1901-04-20 | 1901-04-21 | 1901-04-22 | 1901-04-23 | 1901-04-24 | 1901-04-25 | 1901-04-26 | 1901-04-27 | 1901-04-28 | 1901-04-29 | 1901-04-30 | 1901-05-01 | 1901-05-02 | 1901-05-03 | 1901-05-04 | 1901-05-05 | 1901-05-06 | 1901-05-07 | 1901-05-08 | 1901-05-09 | 1901-05-10 | 1901-05-11 | 1901-05-12 | 1901-05-13 | 1901-05-14 | 1901-05-15 | 1901-05-16 | 1901-05-17 | 1901-05-18 | 1901-05-19 | 1901-05-20 | 1901-05-21 | 1901-05-22 | 1901-05-23 | 1901-05-24 | 1901-05-25 | 1901-05-26 | 1901-05-27 | 1901-05-28 | 1901-05-29 | 1901-05-30 | 1901-05-31 | 1901-06-01 | 1901-06-02 | 1901-06-03 | 1901-06-04 | 1901-06-05 | 1901-06-06 | 1901-06-07 | 1901-06-08 | 1901-06-09 | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK |  |  | START | END | DAYS | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T |  | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P | E | T | K | N | R | L | P
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | NARVA - TAPA - TALLINN PIIRKOND | bar: L
| Ülemiste jaam (Rail Baltic) |  |  | 2023-04-03 | 2023-08-18 | bar: T to L; T to K; T to L; T to K; L to T; R to L; K to L; K to L; K to L; K to L; T; T; T to L; T to L; T to L; K to L
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Aegviidu - Tapa jaamavahe I tee kapitaalremont (pikkrööpa paigaldus, võimalusel ballasterimine) |  |  | 2023-03-27 | 2023-05-14 | bar: T to E; L
| Aegviidu - Tapa jaamavahe II tee kapitaalremont (pikkrööpa paigaldus, võimalusel ballasterimine) |  |  | 2023-05-15 | 2023-08-24 | bar: T to R
| Aegviidu - Tapa jaamavahe I tee kapitaalremont (pikkrööpa paigaldus, võimalusel ballasterimine) |  |  | 2023-08-25 | 2023-09-27 | bar: L; L to N
| Aegviidu- Tapa jaamavahe II tee kapitaalremont (pikkrööpa paigaldus, võimalusel ballasterimine) |  |  | 2023-09-28 | 2023-10-17 | bar: L; R to K
| Tapa jaama kapitaalremont |  |  | 2023-03-15 | 2023-09-05 | bar: N to K
| Aegviidu - Tapa jaamavahe I tee Kontaktvõrgu ehitamine (vundamentide paigaldus ja kontaktvõrgu paigaldus) |  |  | 2023-05-15 | 2023-07-21 | bar: R to L; L
| Aegviidu - Tapa jaamavahe II tee Kontaktvõrgu ehitamine (vundamentide paigaldus ja kontaktvõrgu paigaldus) |  |  | 2023-06-15 | 2023-08-25 | bar: R to L
| Tapa jaama Kontaktvõrgu ehitamine (vundamentide paigaldus ja kontaktvõrgu paigaldus) |  |  | 2023-06-13 | 2024-01-11 | bar: K to N
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | TAPA - TARTU PIIRKOND | [71 empty] | L: 21.00-13.00
| Tapa-Nõmmküla lõigu (kapitaalremont ja kõverate õgvendamine) |  |  | 2023-08-02 | 2023-11-30 | [67 empty] | K: 22.00-06.00; L: R/L; P: P; E: t/p kooskõl. 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00
| Tapa - Tartu Kontaktvõrgu ehitamine (vundamentide paigaldus ja kontaktvõrgu paigaldus) |  |  | 2023-08-01 | 2023-11-21 | bar: K to K
| Nõmmküla jaam (kapitaalremont ja kõverate õgvendamine) |  |  | 2023-08-02 | 2023-08-17 | [67 empty] | K: 22.00-06.00; L: R/L; P: P; E: t/p kooskõl. 22.00-06.00; L: R/L; P: P; K: 22.00-06.00
| Nõmmküla–Tamsalu lõigu (kapitaalremont ja kõverate õgvendamine) |  |  | 2023-08-02 | 2023-11-30 | [67 empty] | K: 22.00-06.00; L: R/L; P: P; E: t/p kooskõl. 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00
| Tamsalu-Kiltsi lõigu (kapitaalremont ja kõverate õgvendamine) |  |  | 2023-08-02 | 2023-11-30 | [67 empty] | K: 22.00-06.00; L: R/L; P: P; E: t/p kooskõl. 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00
| Vägeva jaam (kapitaalremont ja kõverate õgvendamine) |  |  | 2023-08-02 | 2023-08-17 | [67 empty] | K: 22.00-06.00; L: R/L; P: P; E: t/p kooskõl. 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00
| Kaarepere jaam (kapitaalremont ja kõverate õgvendamine) |  |  | 2023-09-01 | 2023-09-18 | [67 empty] | L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00; L: R/L; P: P; K: 22.00-06.00
Sample phase title block | TARTU - VALGA PIIRKOND | bar: L
| Ropka jaam (raudteeülesõidu kapitaalremont) |  |  | 2023-07-03 | 2023-07-05 | bar: L
Task 3 | bar: L
Task 4 | bar: L
Task 5 | bar: L
Sample phase title block | TARTU - KOIDULA PIIRKOND | bar: L
| Põlva jaam (raudteeülesõidu kapitaalremont) |  |  | 2023-07-03 | 2023-07-06 | bar: E to N; L
| Orava jaam (raudteeülesõidu kapitaalremont) |  |  | 2023-07-03 | 2023-07-05 | bar: E to K; L
Sample phase title block | TALLINN-BALTI - KEILA - PALDISKI, - TURBA piirkond | bar: L
| Pääsküla - Keila MIPRO OY (Pääsküla - Keila rongiliiklus telefonsidel) |  |  |  | 2023-04-23 | bar: K to K; L
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Tondi tänava raudteeülesõidu eritasandilise riste rajamine Tallinn-Balti - Pääsküla |  |  | 2023-07-08 | 2023-08-21 | bar: L to P; L to P; L to P; L to P; L to P; L to P; L to P
| Nõmme raudteeülesõidu kapitaalremont |  |  | 2023-07-15 | 2023-07-30 | bar: L to P; L to P; L to P; L
| Vasalemma jaam 3 tee (kapitaalremont) |  |  | 2023-06-01 | 2023-06-30 | bar: R to L; L
| Riisipere jaam 3 tee (kapitaalremont) |  |  | 2023-06-01 | 2023-06-30 | bar: R to L; L
| Vasalemma - Riisipere (kapitaalremont) |  |  | 2023-06-30 | 2023-08-28 | bar: L to P; L to P; L to P; L to P; L to P; L
| Klooga - Klooga-Rand (raudteeülesõidukoha kapitaalremont) |  |  | 2023-07-03 | 2023-07-04 | bar: E to T; L
Note on DG9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06.00 IV tee
Note on DN9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06-00 IV tee
Note on DU9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06.00 V tee
Note on FH9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 00.00-08.00 IV ja V tee
Note on FK9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-08.00 IV ja V tee
Note on GT9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06.00 IV tee
Note on HA9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06.00 IV ja V tee
Note on HH9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06-00 IV ja V tee
Note on HO9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06.00 IV ja V tee
Note on HV9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06.00 IV ja V tee
Note on IK9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kell 00.00-06.00 IV ja V tee
Note on DO10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I peatee
Note on CQ14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tee nr 8 demonteerimine teed nr 10, 12, 14, 16 suletud
Note on GJ14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Depoo suletud teed nr 700, 701, 67 ja 67A, 613 ja 763
Note on HN14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Liiklus Narva suunal suletud 12h pööre nr 7 paigaldus
Note on IJ14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Liiklus Narva suunal suletud 12h pööre nr 1 vahetus
Note on IO14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Liiklus Narva suunal suletud 12h pööre nr 27 eemaldus pööre nr 17 ja 19 kurbelistid
Note on IT14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Liiklus Narva suunal suletud 12h pööre nr 27 eemaldus pööre nr 21 paigaldus uute lõikude ehitus teel nr III ja 4A
Note on JA14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Liiklus Tartu suunal suletud 12 h pööre nr 11 paigaldus tee nr III ja 4A ühendamine Tartu suunaga ülesõidu ehitus liiklus Tartu suunad üle tee nr III
Note on HW20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22.00-06.00
Note on HZ20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IG20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IN20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IU20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JB20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JI20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JP20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JR20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on JW20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JY20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KD20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KK20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KM20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KR20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KT20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KY20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LA20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LF20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LH20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LM20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LO20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LT20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LV20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on MA20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on MC20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on MH20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on MJ20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on HW22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22.00-06.00
Note on IB22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpäevadel kooskõlastamisel 22.00-06.00
Note on IG22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on II22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpäevadel kooskõlastamisega 22.00-06.00
Note on HW23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22.00-06.00
Note on HZ23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IG23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IN23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IU23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JB23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JI23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JP23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JR23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on JW23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JY23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KD23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KK23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KM23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KR23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KT23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KY23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LA23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LF23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LH23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LM23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LO23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LT23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LV23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on MA23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on MC23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on MH23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on MJ23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on HW24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22.00-06.00
Note on HZ24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IG24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IN24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IU24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JB24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JI24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JP24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JR24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on JW24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JY24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KD24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KK24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KM24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KR24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on KT24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on KY24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LA24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LF24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LH24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LM24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LO24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on LT24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on LV24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on MA24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on MC24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on MH24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on MJ24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on HW25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22.00-06.00
Note on HZ25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IG25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IN25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IU25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on IW25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on JB26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JI26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JP26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40 tundi
Note on JR26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tööpaevadel kooskõlastamisega
Note on GX43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HE43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HL43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HS43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HZ43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on IG43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on IN43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HE44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HL44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HS44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on GQ47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on GX47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HE47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HL47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi
Note on HS47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36 tundi

## Üldine graafik
Akende aastaplaani koondtaabel 2023.a.
| jaam/ jaamavahe/ teed | alg | lõpp | kommentaar | aknad | vastutav isik | telegrammi väljumise aeg (reisi) | liiklus häiritud | kokku päevad | sagedus | akna pikkus | Tööde kirjeldus | töövõtja
1 | 9107692 Tartu jaam | 09.01.2023 | 09.03.2023 | jaam |  | K.Arumetsa |  | rongiliiklus katkestamata |  | ööpäevaringselt | 1439 t | Teedevahelise ajutise ning vana platvormi demontaaž | Leonhard Weiss OÜ
2 | 9106557 Nõmmküla jaam | 03.07.2023 | 31.07.2023 | jaam |  | I.Reipõld |  | 2. ja 3. tee on suletud | 12 x 12 t | päevased | 12 t. | Pöörmete nr 2, 4, 3, 1 vahetus, koos raudteede õgvendustega. | hange on planeerimisfaasis | I peatee km 324 pk 1 kuni km 326 pk 5; 2. ja 3. teed - km 325 pk 3 kuni km 324 pk 2
3 | 9106557 Vägeva jaam | 01.08.2023 | 31.08.2023 | jaam |  | I.Reipõld |  | 2. ja 3. tee on suletud | 12 x 12 t | päevased | 12 t. | Pöörmete nr 2, 4, 3, 1 vahetus, koos raudteede õgvendustega. | hange on planeerimisfaasis | I peatee km 360 pk 3 kuni km 362 pk 2; 2. ja 3. teed - km361 pk 1 kuni km 362 pk 1
4 | 9106557 Kaarepere jaam | 01.09.2023 | 31.09.2023 | jaam |  | I.Reipõld |  | 2. ja 3. tee on suletud | 12 x 12 t | päevased | 12 t. | Pöörmete nr 2, 4, 3, 1 vahetus, koos raudteede õgvendustega. | hange on planeerimisfaasis | I peatee km 392 pk 1 kuni km 393 pk 5; 2. ja 3. teed - km 392 pk 2 kuni km 392 pk 3
5 | 9106335 Ropka jaam | 03.07.2023 | 31.10.2023 | raudteeülesõit |  | I. Romandi |  |  | 3 x 12 t | päevased | 12 t. | Ropka raudülesõidukoha remont | hange on planeerimisfaasis | Ropka jaam km 437 pk 1
6 | 9106207 Põlva jaam | 03.07.2023 | 31.10.2023 | raudteeülesõit |  | I. Romandi |  | nädalavahetusel II peatee sulgeda | 4 x 12 t | päevased | 12 t. | Põlva raudteeülesõidukoha remont | hange on planeerimisfaasis | Põlva jaam km 43 pk 7
7 | 9106309 Orava jaam | 03.07.2023 | 31.10.2023 | raudteeülesõit |  | I. Romandi |  |  | 3 x 12 t | päevased | 12 t. | Orava raudteeülesõidukoha remont | hange on planeerimisfaasis | Orava jaam km 74 pk 2
8 | 9106541 Ülemiste jaam | 01.04.2023 | 14.04.2023 | raudteeifrastruktuuri rekonstrueerimine |  | J. Minski |  | IV peatee suletud | 7 x 6 t | öösel | 6 t | Pöörmete ja fooride ümberühendamine | hange on planeerimisfaasis | km110 pk 1 kuni km 112 pk 4
9 | 9107259 Ülemiste jaam | 17.04.2023 | 25.04.2023 | raudteeifrastruktuuri rekonstrueerimine |  | J. Minski |  | V peatee suletud | 7 x 6 t | öösel | 6 t | Pöörmete ja fooride ümberühendamine | hange on planeerimisfaasis | km110 pk 1 kuni km 112 pk 4
10 | 9107290 Ülemiste jaam | 26.05.2023 | 01.06.2023 | raudteeifrastruktuuri rekonstrueerimine |  | J. Minski |  | IV peatee suletud | 3 x 8 t | öösel | 8 t | Pöörmete demonteerimine ja asendamine sirge teelõiguga | hange on planeerimisfaasis | km110 pk 1 kuni km 112 pk 5
[8 empty] | V peatee suletud | 2 x 8 t |  | 8 t | Pöörmete demonteerimine ja asendamine sirge teelõiguga | hange on planeerimisfaasis | km110 pk 1 kuni km 112 pk 6
11 | 9107365 Ülemiste jaam | 29.05.2023 | 03.07.2023 | raudteeifrastruktuuri rekonstrueerimine |  | J. Minski |  | IV peatee suletud | 26 x 6 t | öösel | 6 t | Ajutiste kontaktvõrgu mastide paigaldus ja terminali kaeviku rajamine | hange on planeerimisfaasis | km110 pk 6 kuni km 111 pk 10
12 | 9107476 Ülemiste jaam | 10.07.2023 | 04.08.2023 | raudteeifrastruktuuri rekonstrueerimine |  | J. Minski |  | V peatee suletud | 5 x 6 t | öösel | 6 t | Uute KV vundamentide, mastide ja riiglite paigaldamine | hange on planeerimisfaasis | km 111 pk 10 kuni km 112 pk 4
[8 empty] | IV peatee suletud | 5 x 6 t | öösel | 6 t | Uute KV vundamentide, mastide ja riiglite paigaldamine | hange on planeerimisfaasis | km 111 pk 10 kuni km 112 pk 4
[8 empty] | V ja IV peateed suletud | 10 x 6 t | öösel | 6 t | Riiglite paigaldamine | hange on planeerimisfaasis | km 111 pk 10 kuni km 112 pk 4
13 | 9107604 Ülemiste jaam | 15.08.2023 | 18.08.2023 | raudteeifrastruktuuri rekonstrueerimine |  | J. Minski |  | V ja IV peateed suletud | 4 x 6 t | öösel | 6 t | 131/133 siirde elektrifitseerimine | hange on planeerimisfaasis | km114 pk 8 kuni km 115 pk 1
14 | 9106391 Riisipere jaam | 01.06.2023 | 30.06.2023 | Jaam |  | I. Romandi |  | 3. tee | 1 x 720 t | ööpäevaringselt | 720 t | 3. tee kapitaalremont | hange on planeerimisfaasis | km 53 pk 8 kuni km 54 pk 6
15 | 9106392 Vasalemma jaam | 01.06.2023 | 30.06.2023 | Jaam |  | I. Romandi |  | 3. tee | 1 x 720 t | ööpäevaringselt | 720 t | 3. tee kapitaalremont | hange on planeerimisfaasis | km 67 pk 4 kuni km 68 pk 3
16 | 9106403 Vasalemma - Riisipere | 30.06.2023 | 28.08.2023 | Jaamavahe |  | I. Romandi |  | II tee | 5 x 265 t | ööpäevaringselt | 265 t | kapitaalremont | hange on planeerimisfaasis | km 55,77 kuni km 54,70 ja km 67,116 kuni km 61,20
17 | 9106354 Keila - Klooga jaamavahe | 03.07.2023 | 05.07.2023 | raudteeülesõit |  | I. Romandi |  |  | 3 x 12 t | pole oluline | 12 t | Keila raudteeülesõidukoha remont | hange on planeerimisfaasis | km 2 pk 4
18 | 9106377 Klooga - Klooga-Rand | 03.07.2023 | 04.07.2023 | raudteeülesõit |  | I. Romandi |  |  | 2 x 12 t | pole oluline | 12 t | Klooga - Ranna raudteeülesõidukoha remont | hange on planeerimisfaasis | km 3 pk 6
19 | 9110250 Tallinn-Balti - Pääsküla jaamavahe | 15.07.2023 | 30.07.2023 | raudteeülesõit |  | I. Romandi |  | I ja II teed | 3 x 12 t | pole oluline | 12 t | Nõmme raudteeülesõidukoha remont | hange on planeerimisfaasis | km 97 pk 8
20 | 9107096 Pääsküla - Tallinn-Balti jaamavahe | 08.07.2023 | 31.07.2023 | raudteeülesõit |  | R. Rüütel |  | I peatee | 7 x 5 t | öösel | 5 t | Tondi tänava raudteeülesõidu eritasandilise riste rajamine | hange on planeerimisfaasis
21 | 9107096 Pääsküla - Tallinn - Balti | 05.08.2023 | 21.08.2023 | raudteeülesõit |  | R. Rüütel |  | I peatee | 7 x 5 t | öösel | 5 t | Tondi tänava raudteeülesõidu eritasandilise riste rajamine | hange on planeerimisfaasis
aktsepteeritud
30 | 9103194 Oru jaam | 2022-08-01 | 2022-08-31 | aktsepteeritud | raudteeülesõit |  |  | I.Reipõld |  |  | 3 x 12 t | öised aknad | 12 t. | Oru raudteeülesõidukoha remont | hange on planeerimisfaasis | km 278 pk 7
31 | 9103182 Vaeküla-Rakvere jaamavahe | 2022-08-01 | 2022-08-31 | aktsepteeritud | raudteeülesõit |  |  | I.Reipõld |  |  | 3 x 12 t | öised aknad | 12 t. | Vaeküla raudteeülesõidukoha remont | hange on planeerimisfaasis | km 216 pk 4
32 | 9102842 Rakvere jaam | 2022-05-01 | 2022-05-31 |  | raudteeülesõit |  | 01.05.-31.05.22 | I.Reipõld |  | 2 akna ajal II peatee liikluseks suletud | 1 x 12 t+2x 8 t | öised aknad |  | Rakvere raudteeülesõidukoha remont | Leonhard Weiss OÜ | km 208 pk 10
[10 empty] | 12. tee suletud | 1 x 24 t | ööpäevaringselt
33 | 9102921 Raasiku-Lagedi jaamavahe | 2022-05-01 | 2022-05-31 | aktsepteeritud | raudteeülesõit |  | 01.05.-31.05.22 | I.Reipõld |  | 1 aken I ja II tee liikluseks suletud | 1 x 6 t | öised aknad | 6 t. | Kulli raudteeülesõidukoha remont | Leonhard Weiss OÜ | km 124 pk 7
[10 empty] | I peatee suletud liikluseks | 1 x 12 t+2x 8 t | öised aknad
[10 empty] | II peatee suletud liikluseks | 1 x 12 t+2x 8 t | öised aknad
34 | 9103212 Tapa jaam | 2022-08-01 | 2022-08-31 | aktsepteeritud | raudteeülesõit |  | 01.08.-31.08.22 | I.Reipõld |  |  | 1 x 12 t | öised aknad | 12 t. | Veduridepoo raudteeülesõidukoha remont | hange on planeerimisfaasis | km 205 pk 2
aktsepteeritud
35 | 9102801 Aegviidu - Tapa jaamavahe | 2022-05-01 | 2022-07-31 | aktsepteeritud | II tee kapremont |  | 01.05.-31.07.22 | I.Reipõld |  | II tee liikluseks suletud | 1 x 6576 t | ööpäevaringselt | 6576 t. | II peatee kapitaalremont | hange on planeerimisfaasis
36 | 9102773 Aegviidu - Tapa jaamavahe | 2022-08-01 | 2022-11-30 |  | I tee kapremont |  | 01.08.-30.11.22 | I.Reipõld |  | I tee liikluseks suletud | 1 x 5856 t | ööpäevaringselt | 5856 t. | I peatee kapitaalremont | hange on planeerimisfaasis
37 | Tallinn-Narva, Tallinn - Tartu, Tartu-Koidula, Tartu - Valga |  |  |  | moderniseerimine CCS |  |  | K. Andreitsuk |  | planeerimis faasis